**FIP Name**

**Workplan (Note the start and end dates of the workplan; SFP recommends each workplan is ~12 months in length)**

**Current Date**

**Status of the fishery**

* Brief summary of the fishery evaluation with regard to stock status, governance quality, and environment/biodiversity impacts
* Highlight specific improvement needs identified in the fishery

**Workplan**

* Talk generally about what needs to be done to address the improvement needs

***Example Table***

|  |  |  |  |
| --- | --- | --- | --- |
| Topic/Activity | Deliverables | Deadline | Status |
| FIP participants sign  memorandum of  understanding (MoU) | Signed MOU made public | October 2011 | Completed |
| National management plan | Letter to Ministry  Analysis of national plan  Meeting with Ministry | October 2011  Oct-Nov 2011  Nov-Dec 2011 | Completed  Completed  Completed |
| Influence IOTC | Letter to IOTC  Preparing data submissions to IOTC | October 2011  Mid Oct-Nov 2011 | Completed  Completed |
|  | Participation in IOTC | 8-10 Dec 2011, Seychelles  22-26 April 2012, Australia | Completed  Not completed |
| Analysis of observers data | Analysis of data & report | 2th quarter 2012 | Not completed |
| Selective gears | Choice & testing of hooks  Training for life bycatch release | Mid 2012  Mid 2012 | Not completed  Not completed |
|  |  |  |  |